## Sprint Backlog
Sprint #1 Backlog
Priority | Product backlog items | User story | Story point | Estimate (hours) | Assigned | Status | Comments
1 | Store Stock Item | Warehouse wants to provide inventory stock to HQ | 5 | 20 | All | NOT COMPLETED | In planning phase we have underestimated the size and the complexity of the user stories.
2 | Stock Item List View | Warehouse wants to be able to see their stock | 4 | 16 | All | NOT COMPLETED
3 | Send Employee Data to HQ | Warehouse wants to provide a list of employees to HQ | 5 | 20 | All | NOT COMPLETED
4 | Receive Stock Data | HQ wants inventory from warehouse | 3 | 12 | All | NOT COMPLETED
5 | Receive Emplopyee Data | HQ wants to have a list of employees at warehouse | 3 | 12 | All | NOT COMPLETED
6 | Employee List Creation/ View | HQ wants to have a list of employees in the headquarters | 4 | 16 | All | NOT COMPLETED
24
Sprint #2 Backlog
Priority | Product backlog items | User story | Story point | Estimate (hours) | Assigned | Status | Comments
1 | Store Stock Item | Warehouse wants to provide inventory stock to HQ | 5 | 20 | All | NOT COMPLETED | The reason why the team was unable to complete the tasks is because we have increased the size of the user stories.
2 | Stock Item List View | Warehouse wants to be able to see their stock | 4 | 16 | All | NOT COMPLETED
3 | Send Employee Data to HQ | Warehouse wants to provide a list of employees to HQ | 5 | 20 | All | NOT COMPLETED
4 | Receive Stock Data | HQ wants inventory from warehouse | 3 | 12 | All | NOT COMPLETED
5 | Receive Emplopyee Data | HQ wants to have a list of employees at warehouse | 3 | 12 | All | NOT COMPLETED
6 | Employee List Creation/ View | HQ wants to have a list of employees in the headquarters | 4 | 16 | All | NOT COMPLETED
24
Sprint #3 Backlog
Priority | Product backlog items | User story | Story point | Estimate (hours) | Assigned | Status | Comments
1 | Store Stock Item - Warehouse | As a manager at the Warehouse, I would like to be able to store stock items so that I can have an accurate stock inventory. | 6 | 24 | Florin | COMPLETED
2 | Stock Item List View - Warehouse | As a manager at the Warehouse, I would like to be able to check my stock inventory so that I can have an overview. | 5 | 20 | Florin | COMPLETED
3 | Store Employee Item - Warehouse | As a manager at the Warehouse, I would like to be able to store my employees so that I can have an overview of my active employees. | 6 | 24 | Jaume | COMPLETED
4 | Employee Item List View - Warehouse | As a manager at the Warehouse I would like to be able to see my list of active employees so that I can have an overview. | 5 | 20 | Jaume | COMPLETED
5 | Request products from HQ | As a manager at the Warehouse, I need to request products from Headquarters to keep my stock levels optimal. | 3 | 12 | Kenneth | NOT COMPLETED | Issues with interactions between database
6 | Store Employee Item - HQ | As a manager at the Headquarter, I would like to store my list of employees with info so I can have a clear overview over my human resources. | 2 | 8 | Dave | COMPLETED
7 | Previous deliveries log | As a manager at the Headquarter, I want to be able to see the previous deliveries to the Warehouse so I can have an overview over this business process | 3 | 12 | Jaume | COMPLETED
8 | HQ check Employee Item at Warehouse | As a manager at the Headquarter, I would like to be able to store stock items so that I can have an accurate stock inventory. | 1 | 4 | Dave | COMPLETED
9 | HQ check Stock Item at Warehouse | As a manager at the Headquarter, I would like to be able to check my stock inventory so that I can have an overview. | 1 | 4 | Dave | COMPLETED
10 | System notifies on minimum stock | As a manager at the Warehouse, I need to be notified on maximum stock on requests so I don't exceed capacity. | 3 | 12 | Kenneth | NOT COMPLETED | Issues with obtaining a scalable list in the view / Issues with planning and time management
11 | System notifies on maximum stock | As a manager at the Warehouse, I need to be notified on minimum stock so I don't lack stock inventory for deliveries. | 3 | 12 | Kenneth | NOT COMPLETED
Sprint #4 Backlog
Priority | Product backlog items | User story | Story point | Estimate (hours) | Assigned | Status | Comments
1 | Request products | As a manager at the Warehouse, I need to request products from Headquarters to keep my stock levels optimal. | 5 | 20 | Jaume | COMPLETED
2 | Remove employee | As a manager at the Warehouse, I want to be able to edit my list of employees so that I can remove non-working employees. | 4 | 16 | Dave | COMPLETED
3 | Delete Stock Item | As a manager at the Warehouse I would like to delete Stock Items from Warehouse inventory so that I can have an accurate inventory | 4 | 16 | Florin | COMPLETED
4 | Delete Stock Item | As a manager at the Headquarter I would like to delete Stock Items from Headquarter inventory so that I can have an accurate inventory. | 4 | 16 | Kenneth | COMPLETED
5 | Remove employee | As a manager at the Headquarter, I want to be able to edit my list of employees so that I can remove non-working employees. | 4 | 16 | Jaume | COMPLETED
6 |  | Process Report | 3 | 12 |  | COMPLETED
Sprint #5 Backlog
Priority | Product backlog items | User story | Story point | Estimate (hours) | Assigned | Status | Comments
1 |  | Process Report | 2 | 8 | Florin | COMPLETED
2 | Request and receive | As a manager at the Shop, I need to request and receive products from Warehouse so I can maintain to avoid lack of inventory. | 7 | 28 | Jaume | COMPLETED
3 | Input and Store sales | As a manager at the Shop, I would like to input and store all my sales units so I can have an overview of my Shop's sales efficiency | 7 | 28 | Dave | COMPLETED
4 | See Stock | As a manager at the Shop, I would like to be able to see all my stored stock items so I can have an overview of my stock inventory levels. | 4 | 16 | Kenneth | COMPLETED
5 | Add Stock Item to Inventory | As a manager at the Shop, I would like to be able to add items to Stock Inventory so I would be able to order them from Warehouse. | 4 | 16 | Florin | COMPLETED
Sprint #6 Backlog
Priority | Product backlog items | User story | Story point | Estimate (hours) | Assigned | Status | Comments
1 | Process Report | Process Report | 2 | 8 | Florin | COMPLETED
2 | Sales analysis | As a manager at Shop, I would like a sales analysis based on sales so I can have data to later report to Headquarter. | 5 | 20 | Dave | COMPLETED
3 | Delivery log | As a manager at the Shop, I need to have an overview of previous deliveries from the Warehouse so I can have an overview. | 3 | 12 | Kenneth | COMPLETED
4 | Delivery log | As a manager at the Warehouse, I want to be able to check the previous deliveries from Headquarter to Warehouse so I can have an overview. | 3 | 12 | Jaume | COMPLETED
5 | Delivery log | As a manager at the Warehouse, I would like to check the previous deliveries from the Warehouse to the Shop so I can decide on future requests of products from HQ. | 3 | 12 | Kenneth | COMPLETED
6 | Delivery log | NEW ->> As a manager at the Headquarter, I would like to be able to see all deliveries between Shop and Warehouse so I can have control of it and overview | 4 | 16 | Dave | COMPLETED
7 | Project Report | Project Report | 4 | 16 |  | COMPLETED
Sprint #7 Backlog
Priority | Product backlog items | User story | Story point | Estimate (hours) | Assigned | Status | Comments
1 | View Stock Inventory | As a manager at the Headquarter, I would like to see the Stock Inventory at the Shop so I can have an overview. | 1 | 4 | All | COMPLETED
2 | View Stock Inventory | As a manager at the Headquarter, I would like to see the Stock Inventory at the Warehouse so I can have an overview. | 1 | 4 | All | COMPLETED
3 | View Employee List | As a manager at the Headquarter, I would like to see the list of employees from the Warehouse so I can have an overview. | 1 | 4 | All | COMPLETED
4 | View Employee List | As a manager at the Headquarter, I would like to see the list of employees from the Shop so I can have an overview. | 1 | 4 | All | COMPLETED
5 | Chat | As a manager at the Headquarter, I would like to be able to communicate with all managers so that we have an efficient communication. | 4 | 16 | All | COMPLETED
6 |  | Project Report | 8 | 32 | All | COMPLETED
7 |  | Process Report | 8 | 32 | All | COMPLETED

## Product Backlog
# | WAREHOUSE | Priority
1 | As a manager at the Warehouse, I need to request products from Headquarters to keep my stock levels optimal. | 2
2 | As a manager at the Warehouse, I need to be notified on maximum stock on requests so I don't exceed capacity. | 2
3 | As a manager at the Warehouse, I need to be notified on minimum stock so I don't lack stock inventory for deliveries. | 2
4 | As a manager at the Warehouse, I need to check previous deliveries to the Shop so I can have an overview of deliveries. | 2
5 | As a manager at the Warehouse, I want to be able to check the previous deliveries from Headquarter to Warehouse so I can have an overview. | 2
6 | As a manager at the Warehouse, I want to be able to confirm the deliveries that have been sent from HQ to Warehouse to avoid any misunderstandings. | 3
7 | As a manager at the Warehouse, I would like to check the deliveries in progress to the Shop so I can have an overview on the process. | 3
8 | As a manager at the Warehouse, I would like to check the previous deliveries from the Warehouse to the Shop so I can decide on future requests of products from HQ. | 3
9 | As a manager at the Warehouse, I would like to check the status on the amount of expired products so I can make my stock inventory more efficient and reduce waste. | 3
10 | As a manager at the Warehouse I would like to see the work history and performance of my employees so I can keep track on productivity. | 3
11 | NEW-> As a manager at the Warehouse, I want to be able to edit my list of employees so that I can remove non-working employees. | 2
12 | NEW ->> As a manager at the Warehouse I would like to delete Stock Items from Warehouse inventory so that I can have an accurate stock inventory. | 1
13 | As a manager at the Warehouse, I would like to be able to store stock items so that I can have an accurate stock inventory. | 1
14 | As a manager at the Warehouse, I would like to be able to check my stock inventory so that I can have an overview. | 1
15 | As a manager at the Warehouse I would like to be able to see my list of active employees so that I can have an overview. | 1
16 | As a manager at the Warehouse, I would like to be able to store my employees so that I can have an overview of my active employees. | 1
# | HEADQUARTERS | Priority
1 | As a manager at the Headquarter, I want to check the stock inventory at the Warehouse to have control over process or to replace functions for holidays | 2
| As a manager at the Headquarter, I would like to see the Stock Inventory at the Shop so I can have an overview. | 2
2 | As a manager at the Headquarter, I would like to see the Stock Inventory at the Warehouse so I can have an overview. | 2
3 | As a manager at the Headquarter, I would like to store my list of employees with info so I can have a clear overview over my human resources. | 1
4 | As a manager at the Headquarter, I would like to be able to edit my list of employees so that I can remove non-working employees. | 2
5 | As a manager at the Headquarter, I want to be able to see the previous deliveries to the Warehouse so I can have an overview over this business process | 2
6 | As a manager at the Headquarter, I want to be able to see the deliveries in progress to the Warehouse so I can have an overview over this business process | 3
7 | As a manager at the Headquarter, I would like to be able to check the sales from Shop so I can have an overview. | 1
8 | As a manager at the Headquarter, I would like to see the list of employees from the Warehouse so I can have an overview. | 2
9 | As a manager at the Headquarter, I would like to see the list of employees from the Shop so I can have an overview. | 2
10 | As a manager at the Headquarter, I would like a way to predict the upcoming sales at the Shop so I can ensure the availability of the products | 3
11 | As a manager at the Headquarter, I would like a way of obtaining the sales performance analysis from the Shop so I can ensure profitability/ product category. | 3
12 | As amanager at the Headquarter, I would like to implement a discount system for all companie's employee's whenever they make purchases in the shop so I can increase employee's benefits and satisfaction | 3
13 | As a manager at the Headquarter, I would like to obtain product performance analysis so I can ensure profitability/ product. | 2
14 | As a manager at the Headquarter, I would like to have an overview over the deliveries in progress so I can keep an accurate track on my business process. | 2
15 | NEW ->> As a manager at the Headquarter I would like to delete Stock Items from Headquarter inventory so that I can have an accurate stock inventory. | 2
16 | NEW-> As a manager at the Headquarter, I want to be able to edit my list of employees so that I can remove non-working employees. | 2
17 | NEW ->> As a manager at the Headquarter, I would like to be able to communicate with all managers so that we have an efficient communication. | 2
18 | As a manager at the Headquarter, I would like to be able to store stock items so that I can have an accurate stock inventory. | 1
19 | As a manager at the Headquarter, I would like to be able to check my stock inventory so that I can have an overview. | 1
20 | NEW ->> As a manager at the Headquarter, I would like to be able to see all deliveries between Shop and Warehouse so I can have control of it and overview | 2
# | SHOP | Priority
1 | NEW ->> As a manager at the Shop, I would like to input and store all my sales units so I can have an overview of my Shop's sales efficiency | 1
2 | As a manager at the Shop, I would like to be able to see all my stored stock items so I can have an overview of my stock inventory levels | 1
3 | As a manager at the Shop, I would like to store my employee info so I can fulfill human resources requirements | 1
4 | As a manager at the Shop, I would like to see the list of employees from my Shop for further reporting or overview. | 1
5 | As a manager at the Shop, I would like to be able to edit and remove employees so I can maintain a clean database of active employees | 2
6 | As a manager at the Shop, I would like to be able to see my employees history so I can have an overview over employees productivity | 3
7 | As a manager at the Shop, I need to request products and receive from Warehouse so I can maintain to avoid lack of inventory. | 2
8 | As a manager at the Shop, I need to have an overview of previous deliveries from the Warehouse so I can have an overview. | 2
9 | As a manager at the Shop, I would like to see my stock inventory at the shop so I can have an overview | 1
10 | NEW -> As a manager at the Shop, I would like to be able to add items to Stock Inventory so I would be able to order them from Warehouse. | 1
11 | NEW ->>> As a manager at Shop, I would like a sales analysis based on sales so I can have data to later report to Headquarter. | 2